## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the proces and include a detailed description of every step. Add reasoning on why you took certain descisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description
Planning and researching | 1 | 2020-11-12 | Planning how I am going to spend my time on the project by estimating the different tasks to perform and how long they will take, basic research on maze generation algorithms.
Implement basic architecture and DFS algorithm | 2 | 2020-11-12 | Creating graph, node and edge classes. Implementing a DFS algorithm to randomly generate a maze. DFS was chosen because I've studied it in class and it seemed relatively easy to implement. It takes a graph as an input, in which nodes are disposed in a grid. Each node is connected to its right, left, upper and lower neighboors. DFS doesn't directly output a set of edges but the order in which nodes are visited, which then can be used to reconstruct the spanning tree
Implement a script that displays the created maze | 2 | 2020-11-13 | Implementing a script to display the maze in Unity. The previous DFS algorithm outputs a list of edges that constitute the path accross the maze. I created a script that creates a wall in Unity for all edges that are not part of the path. I made several basic mistakes and I spent some time debugging.
Added exterior walls to the maze | 1 | 2020-11-13 | Added walls to the exterior of the maze, for the moment, the maze is generated and then the exterior walls spawn based on the position of the maze. At this point, the entire maze is generated in the Editor, but it's position isn't adjusted to the camera
Adjusting walls to the size of the screen | 2 | 2020-11-14 | By using the size of the screen, the maze is correctly placed on the camera. The camera was switched to orthographic view, because it was much more complicated to correctly place objects in perspective view. Unfortunately, this means that the maze will be displayed in 2D. Minor setback, small holes can appear between walls
Implementing a basic UI | 1 | 2020-11-14 | I added a basic UI : the user can specify the desired height and width of the graph in an input field. He can then press a button to generate the maze. When the maze is generated, the menu disappears and a small menu button appears in the upper left corner. By clicking on this button, the previous menu appears again. The UI works entirely with on click commands and not with scripts. This made it easier and faster to implement a basic UI. At this point, all main criteria of the project have been fulfilled.
Cleaning up and fixing minor issues | 1 | 2020-11-14 | Cleaning up of the previous code, debugging commands were removed as well as parts that are not useful anymore, correction of the holes in wall issue, it was due to a float conversion error and a problem with the placement of the light.
Implementing Kruskal algorithm | 2 | 2020-11-15 | I added another maze generating algorithm and a dropdown to the menu to select the desired algorithm to generate the maze. I realized that I needed to rewrite some functions that I already used (the remove doubles function for example) and I corrected my script organization.
Improving UI | 1 | 2020-11-15 | I added basic animations to the UI by using tweening. I had no experience with it before so I watched the following tutorial : https://www.youtube.com/watch?v=Ll3yujn9GVQ&t=138s&ab_channel=GameDevGuide. It seemed like a quicker way to add animations than using animators, so I decided to try it. I also added a button that memorizes the last algorithm, height and width of the maze chosen to regenerate a maze with the same parameters
Trying to create a controlable player to explore the maze | 1 | 2020-11-15 | I watched tutorials to implement a player that could explore the maze but I realized that at his point it would take too much time to finish
Writing the development documentation and final cleanup | 1 | 2020-11-15 | I wrote the development documentation as a powerpoint that explains the solution I chose. I then reviewed all my scripts one last time before sending them.
Total amount of hours | 15